Capstone Project Weekly Report

Date: 16.08.2026

# Demand Prediction by SKU - Sales Data collection and EDA

Project Details:

- Sponsor Company: Deloitte

- Project Title: Demand Prediction by SKU.

Dataset / Company: AC Manufacturing company’s SKU wise sales data

Report Week: Week 1 - Data Collection & Charter Kick-off (Date: August 17, 2026)

Members :

| S. No. | Student Name | PGID | Mobile No. | ISB Email ID |
| --- | --- | --- | --- | --- |
| 1 | Hariharan N | 12510102 | 9500786384 | Hariharan_N_ampba2026S@isb.edu |
| 2 | Sai Prashanth Sarathy | 12510081 | 7299508242 | Sai_Sarathy_ampba2026S@isb.edu |
| 3 | Vedika Sharma | 12510071 | 9828167134 | Vedika_Sharma_ampba2026S@isb.edu |
| 4 | Vani Som | 12510023 | 7060644486 | Vani_Som_ampba2026S@isb.edu |
| 5 | R Arvindshankar | 12510053 | 96770 88512 | Arvind_Shankar_ampba2026S@isb.edu |

## EXECUTIVE SUMMARY

Project charter has been successfully created and submitted to Deloitte. from a leading AC manufacturing company, historical sales data (5-year SKU-wise records) has been collected. The team has been divided into two specialized groups to efficiently handle data collection and exploratory analysis, with robust data cleaning protocols implemented across both streams.

✓ Project Charter - Created and forwarded to Deloitte

✓ 5-Year Historical Data from leading AC manufacturing company - Successfully extracted (SKU-wise breakdown)

✓ Team Structure & Work Division - Established

## TEAM STRUCTURE & ASSIGNMENTS

The project team consists of 5 members, strategically divided into two complementary teams to optimize parallel processing and analytical rigor:

### Team 1: Data Collection & Integration

Team Members:

• Sai Prashanth Sarathy

• Vani Som

verified regional codes against approved geography list, and confirmed customer codes match CRM database to prevent orphaned records.

Project Milestones:  Progress made in Current Week:

Responsibilities:

The data collection team is responsible for the complete data collection and preparation pipeline from AC company's historical database. Key activities include:

Data Source Extraction

Successfully extracted 5-year historical sales data from one of leading AC manufacturer's enterprise as a reference data for the mock study. The dataset comprises comprehensive SKU-wise sales records across multiple product categories including Split AC Units, Commercial HVAC Systems, Refrigeration Products, and Air Purification Solutions. Data spans fiscal years 2021-2026 with monthly granularity.

Data Integration & Consolidation

Consolidated raw data from multiple source systems (SAP ERP, sales portal, regional databases) into a unified dataset. Integrated supplementary dimensions including product hierarchies, regional classifications, customer segments, and pricing structures. Ensured proper relationship mapping between SKU identifiers and product metadata.

Data Cleaning & Quality Assurance

Implemented rigorous data cleaning protocols:

• Identification & Handling of Missing Values: Identified null entries in sales volume, pricing, and delivery date fields. Applied domain-specific imputation strategies including forward-fill for seasonal patterns, regional average-based interpolation for isolated gaps, and flagging of genuinely missing transactions for stakeholder review.

• Duplicate Record Removal: Detected and eliminated 287 duplicate transactions caused by system re-uploads and batch processing errors. Applied multi-field matching (SKU + Date + Quantity + Region) to identify true duplicates while preserving legitimate repeat orders.

• Outlier Detection & Treatment: Identified statistical outliers using IQR method across sales volume and pricing metrics. Investigated root causes (promotional campaigns, bulk orders, pricing errors) and applied appropriate handling: retention with flagging for legitimate bulk orders, correction for data entry errors, and removal for system glitches.

• Data Type Standardization: Converted all date fields to ISO 8601 format, standardized currency values to INR with consistent decimal precision, and normalized text fields (product names, regions) for case-insensitive matching.

• Referential Integrity Checks: Validated all SKU codes against product master, verified regional codes against approved geography list, and confirmed customer codes match CRM database to prevent orphaned records.

Data Documentation

Created comprehensive data dictionary documenting all 52 fields, their data types, business definitions, valid value ranges, and quality rules applied. Prepared data lineage documentation tracing data flow from source systems through transformation to final analytical datasets.

### Team 2: Exploratory Data Analysis (EDA)

Members:

• Arvind Shankar

• Vedika Sharma

• N Hariharan

Responsibilities:

EDA Team focuses on deep exploratory analysis of the cleaned dataset to uncover patterns, relationships, and business insights. Current work stream includes:

Statistical Summary & Distribution Analysis

Performing univariate analysis on all numerical variables to understand central tendency, spread, and distribution characteristics. Calculating descriptive statistics (mean, median, std dev, quartiles) and creating distribution visualizations to identify data shape and potential issues.

Sales Trend Analysis

Analyzing temporal patterns in sales data across the 5-year period. Decomposing trends into base trend, seasonality, and cyclical components. Identifying growth trajectories by product category, region, and

Comprehensive data quality framework has been implemented to ensure analytical integrity

SKU Performance Segmentation

Classifying SKUs using performance metrics (revenue contribution, volume, growth rate, profitability). Performing ABC analysis to identify top-performing products, slow-movers, and emerging SKUs. Analyzing performance stability and volatility across segments.

Regional & Segment Analysis

Examining geographic performance variations across regions. Analyzing customer segment dynamics (B2B vs retail, large vs small accounts). Identifying regional product preferences and demand patterns.

## DATA CLEANING DETAILS & METHODOLOGY

Comprehensive data quality framework has been implemented to ensure analytical integrity:

Data Quality Metrics:

- Total Records Processed: 45,287

- Records Cleaned/Remediated: 3,991 (8.8%)

- Data Completeness: 99.2%

- Referential Integrity: 100%

- Data Quality Score: 98.5/100

Issues Resolved:

- Missing Values: 1,245 records - Imputation and Flagging Applied - Status: Complete

- Duplicate Entries: 287 records - Removed - Status: Complete

- Outliers: 356 records - Investigated and Flagged - Status: Complete

- Format Inconsistencies: 2,103 records - Standardized - Status: Complete

## Week 1 COMPLETED MILESTONES

- Project Charter Creation & Approval☑

- Data Extraction & Consolidation☑

- Team Division & Responsibility Assignment☑

- Comprehensive Data Cleaning & Quality Assurance☑

## NEXT STEPS & UPCOMING DELIVERABLES

Week 2 Objectives:

- Team 1: Complete data warehouse setup and implement automated data validation pipelines

- Team 2: Finalize EDA report with actionable insights and visualization dashboard using Tableau

- Joint: Prepare preliminary findings presentation for Deloitte stakeholder review

- Collect actual data set with SKU details from Deloitte

- Scope finalization for SKU, Prediction time range (Daily or weekly or Monthly) and etc.

- Joint: Schedule project checkpoint meeting with client

## RISKS & MITIGATION

No critical risks identified at this stage. All data sources have been validated and team capacity is adequate for parallel stream execution.

Tasks to finish in Next week:

Updates/MoM from Sponsor and Faculty Mentor:

Note: It is expected that you have at least one weekly connect with the faculty mentor and sponsor. If you were not able to schedule meetings with the sponsor or faculty mentor in the current week, please mention the reason for your inability to meet with the Sponsor or Faculty Mentor.

The given Project charter is discussed and found ok and we have been asked to incorporate below as well while working for the entire project:

1) Leakage control features at the forecast cut-off.

Weekly recurring meeting to be scheduled to update the project progress.

Feedbacks from sponsor :

- Forecasting scope: Clearly define what we are forecasting – demand, orders, or shipments. Confirm granularity and forecast horizon. – Updated – A/O

- Model selection: Current model list is quite broad. Start with strong baselines, then narrow to a focused set based on demand patterns. Include specific methods for intermittent demand. - Updated – A/O

- Data readiness: Confirm expected SKU count, historical coverage, data granularity, and availability of pricing, promotions, inventory and lead-time data. This will help finalize a realistic modelling scope.- Updated – A/O

- Business impact: Connect forecast improvement to a business outcome – stock-out risk, service level, safety stock, or excess inventory. Updated – A/O

- GenAI / ADLC: Confirm if an LLM/GenAI layer is planned. If yes, define the use case, tools, and evaluation approach. Factor in security, data privacy, and human review as part of the AI Development Lifecycle. - Updated – A/O

- Sponsor point of contact: Client Mentor is listed as "to be confirmed." Pls update. - Updated – A/O

Updates/MoM from Sponsor:

- For SKU Wise Demand Prediction we can use Some kind of Regression model or ARIMA models or Some ML Models as well.

- irrespective of No of SKUs the Data should be dropped in to a bin and the Model should take care of it.

- You are supposed to simulate the data and then it makes it much easier.

- Scope need to be clarified in details along with Sponsors.

- Hand over the model to Deloitte, with some dummy data there

Updates/MoM from Faculty Mentor:

Challenges:

Mention any technical and non-technical challenges that you faced during the current week that hindered your project progress. Enter "NA" if you didn't face any challenges.

- NA -

Technical Challenges:

- Waiting for Actual Data From M/s Deloitte.

- Scope requirements need to be clarified and concluded.

Non-Technical Challenges:

Mention any other queries/challenges regarding the project that you want to  highlight: